## Sheet1
PROJECT NAME: AUTOMATED HOTEL RESERVATION SYSTEM FOR AZURE CREST HOTEL | Start Date | End Date | Status
|  |  |  | SEPTEMBER | [31 empty] | OCTOBER
[11 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8
|  |  |  | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu
 | time axis 2023-09-01 to 2023-10-26
Project Kick-off Meeting | 2023-09-02 | 2023-09-02 | Completed | bar: 2023-09-02
Project plan Documentation | 2023-09-02 | 2023-09-07 | Completed | bar: 2023-09-02 to 2023-09-07
Sponsor approval of Project Plan | 2023-09-08 | 2023-09-15 | Completed | bar: 2023-09-08 to 2023-09-15
Project RACI | 2023-09-05 | 2023-09-11 | Completed | bar: 2023-09-05 to 2023-09-11
Sponsor Approval of RACI | 2023-09-08 | 2023-09-15 | Completed | bar: 2023-09-08 to 2023-09-15
High Level Requirement Gathering Workshop | 2023-09-02 | 2023-09-02 | Completed | bar: 2023-09-02
Use Case Diagram | 2023-09-10 | 2023-09-17 | Completed | bar: 2023-09-10 to 2023-09-17
Sponsor Approval of Use case Diagram | 2023-09-13 | 2023-09-18 | Completed | bar: 2023-09-13 to 2023-09-18
Use Case Documentation | 2023-09-10 | 2023-09-17 | Completed | bar: 2023-09-10 to 2023-09-17
Sponsor Approval for Use case Documentation | 2023-09-13 | 2023-09-18 | Completed | bar: 2023-09-13 to 2023-09-18
Process Flow Diagram Documentation | 2023-09-10 | 2023-09-17 | Completed | bar: 2023-09-10 to 2023-09-17
Sponsor Approval for Process Flow Documentation | 2023-09-13 | 2023-09-18 | Completed | bar: 2023-09-13 to 2023-09-18
Swim Lane Diagram Documentation | 2023-09-10 | 2023-09-17 | Completed | bar: 2023-09-10 to 2023-09-17
Sponsor Approval for Swim Lane | 2023-09-13 | 2023-09-17 | Completed | bar: 2023-09-13 to 2023-09-18
Functional Requirement Documentation | 2023-09-16 | 2023-09-29 | Completed | bar: 2023-09-16 to 2023-09-29
Non-Functional Requirement Documentation | 2023-09-22 | 2023-10-06 | Completed | bar: 2023-09-22 to 2023-10-06
Sponsor's Review session of Functional & Non-Functional Requirement | 2023-10-07 | 2023-10-10 | Completed | bar: 2023-10-07 to 2023-10-10
BRD Documentation | 2023-10-11 | 2023-10-16 | Completed | bar: 2023-10-11 to 2023-10-16
Agile User Story & Acceptance Criteria | 2023-09-29 | 2023-10-12 | Completed | bar: 2023-09-29 to 2023-10-12
Sponsors Approval for Requirement Documentation | 2023-10-14 | 2023-10-19 | Completed | bar: 2023-10-14 to 2023-10-19
Development/Unit Testing | 2023-09-29 | 2023-10-12 | Completed | bar: 2023-09-29 to 2023-10-12
Preparing for Testing (Test Cases) | 2023-10-06 | 2023-10-19 | Completed | bar: 2023-10-06 to 2023-10-19
Defect/Bug Management Documentation a. Defect Management Lifecycle | 2023-10-06 | 2023-10-19 | Completed | bar: 2023-10-06 to 2023-10-19
Severity Matrix | 2023-10-12 | 2023-10-18 | Completed | bar: 2023-10-12 to 2023-10-18
QA Testing | 2023-10-13 | 2023-10-19 | Completed | bar: 2023-10-13 to 2023-10-19
Defect Resolution from QA Testing | 2023-10-16 | 2023-10-19 | Completed | bar: 2023-10-16 to 2023-10-19
Requirement Traceability Matrix | 2023-10-16 | 2023-10-20 | Completed | bar: 2023-10-16 to 2023-10-20
Sponsor Approval for RTM | 2023-10-14 | 2023-10-21 | Completed | bar: 2023-10-14 to 2023-10-21
Defect Tracking Documentation | 2023-10-13 | 2023-10-17 | Completed | bar: 2023-10-13 to 2023-10-17
Sponsor Approval for DTD | 2023-10-14 | 2023-10-18 | Completed | bar: 2023-10-14 to 2023-10-18
Sponsors GO / NO GO Decision - Presentation | 2023-10-13 | 2023-10-19 | Completed | bar: 2023-10-13 to 2023-10-19
GO LIVE - Deployment | 2023-10-20 | 2023-10-26 | Completed | bar: 2023-10-20 to 2023-10-26

## Sheet2
2020
APRIL | [27 empty] | MAY | [30 empty] | JUNE | [29 empty] | JULY
Week 1 | [9 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Wek 14 | [6 empty] | Week 15
 | time axis 2020-04-03 to 2020-07-19