## RACI MATRIX
RACI MATRIX
Project Activities/Deliverables | Sponsors | Project Manger | Senior Business Analyst | Business Analyst | Developers | Testers | Business
Project Kick-off Meeting | C | C | A | R | I | I | C
Project plan Documentation | C | C | A | R | I | I | I
Sponsor approval of Project Plan | I | A | R | R | I | I | C
Project RACI | I | C | A | R | I | I | I
Sponsor Approval of RACI | I | A | R | R | I | I | C
High Level Requirement Gathering Workshop | I | C | A | R | I | I | C
Use Case Diagram | I | C | A | R | I | I | I
Sponsor Approval of Use case Diagram | I | A | R | R | I | I | C
Use Case Documentation | I | C | A | R | I | I | C
Sponsor Approval for Use case Documentation | I | A | R | R | I | I | I
Process Flow Diagram Documentation | I | C | A | R | I | I | C
Sponsor Approval for Process Flow Documentation | I | A | R | R | I | I | I
Swim Lane Diagram Documentation | I | C | A | R | I | I | I
Sponsor Approval for Swim Lane | I | A | R | R | I | I | I
Functional Requirement Documentation | I | C | A | R | C | I | C
Non-Functional Requirement Documentation | I | C | A | R | C | I | C
Agile User Story & Acceptance Criteria | i | C | A | R | I | I | C
Sponsor's Review session of Functional & Non-Functional Requirement | I | A | R | R | I | I | I
BRD Documentation | I | C | A | R | I | I | C
Sponsors Approval for Requirement Documentation | I | A | R | R | I | I | I
Development/Unit Testing | I | C | I | A | R | I | I
Preparing for Testing (Test Cases) | I | C | A | R | C | R | I
Defect/Bug Management Documentation a. Defect Management Lifecycle | I | C | A | R | C | R | I
Severity Matrix | I | C | A | R | C | C | I
QA Testing | I | C | A | R | C | R | I
Defect Resolution from QA Testing | I | C | A | R | R | R | I
Requirement Traceability Matrix | I | C | A | R | I | I | I
Sponsor Approval for RTM | I | A | R | R | I | I | I
Defect Tracking Documentation | I | C | A | R | C | C | I
Sponsor Approval for DTD | I | A | R | R | I | I | I
Sponsors GO / NO GO Decision - Presentation | A | C | R | R | I | I | C
GO LIVE - Deployment | A | C | R | R | R | I | C